## Sheet1
Compliance Monitoring of Bat Organisational Licences issued to LMJV
| Under the relevant Organisational Licence: | WML-OR52- South Cubbington | WML-OR53- Kenilworth | WML-OR54 - Fulfen | WML-OR55- Ash Beds | WML-OR56 - Marlowes
1 | What dates did licensable works start? | 1/07/2020 - GI low level disturbance/clearance only | 2020-04-03 | N/A | 2020-06-03 | 2020-04-09
2 | Please confirm if all of the rescue bat boxes and have been installed, and if any additional ones have been required? | 54 boxes erected | 117 erected, includes 2 x additional bat boxes for minimum required (115 required) | N/A | 35 erected pre works as required- 2 x rocket boxes erected during works | 84 erected, no additional erected yet
3 | How many trees have been felled to date ? Please include details of the final tree potential categorisations post updated aerial inspection. | No PRF trees felled- not due until September 2020- Disturbance only | 20 High, 53 Moderate, 121 Low, 1058 Negligible | N/A | 5 Confirmed, 15 High, 39 Moderate, 101 Low, 334 Negligible | 6 Confirmed, 36 High, 107 Moderate, 162 Low, 679 Negligible
4 | How many have been subject to aerial inspections? Of the trees subject to aerial inspection, how many were considered to have been fully inspected? | As required to check for maternity roosts in the vicinty of works- ongoing | 352 felled trees have been subject to aerial inspection. Including some trees which were negligible but needed to be confirmed. | N/A | 260 felled trees have been subject to aerial inspection. Including some trees which were negligible but needed to be confirmed. | 443 felled trees have been subject to aerial inspection. Including some trees which were negligible but needed to be confirmed.
5 | Have any difficulties in inspecting PRFs prior to fell been experienced so far? | Yes some trees have been identified as unsafe and a new route has been found to avoid area | Yes some PRF cannot be fully inspected, and have been worked around until soft felling can be undertaken | N/A | All PRFs were able to be fully inspected except 2 trees below | Yes some PRF cannot be fully inspected, and have been worked around until soft felling can be undertaken
6 | Of the trees that been felled how many have been considered unsafe to climb and the destructive search procedure as per condition B9 been used. | N/A | 25 Trees which have been designated to be destructively searched were not completed due to weather constraints. | N/A | 2 trees destructively searched in June 2020 | 6 Trees which have been designated to be destructively searched were not completed due to weather constraints.
7 | Has the timeframe for feeling tress as stated in condition B6 been achievable so far? | N/A | Yes | N/A | Yes | Yes
8 | Have any bats been encountered so far during the tree clearance works? If so, and in accordance with table 3 on Annex B, please provide details on the species, number of individuals encountered and location. If encountered, have any of these been injured and required to be taken into care. | No | Attached report | N/A | Attached report | Attached report
9 | Of the bats encountered have any been handled/removed from the roost? If so, and in accordance with table 3 on Annex B, please provide details on the species, number of individuals and location. If handled/removed, have any of these been injured and required to be taken into care. | N/A | Attached report | N/A | Attached report | Attached report
10 | Have any new roosts been identified? If so, and in accordance with table 3 on Annex B, please provide details on the species, number of individuals encountered and location. | No | Yes - 2 x daubenton's day roosts- encounter report | N/A | 5 day roosts - common pipistrelle and natterer's - encounter report | 13 day roosts encountered - 5 bat species - encounter report
11 | Have any of the trees previously categorised as High or Moderate since had their status down graded? | TBC | TBC | N/A | TBC | TBC
12 | Have exclusion methods been used on confirmed roosts, or high or moderate potential trees- if so please provide a copy of the written records that are kept as part of condition B11. | N/A | One exclusion of single a single bat | N/A | 3 exclusions in June of single bats - see reports | One exclusion - see attached reports
13 | Given the current work rate, is there a proposed completion date for the tree clearance works? | Low level disturbance at this stage - full works to proceed 1 Sep 2020 to complete Autumn 20 (aligned to work schedule). | Licensable works paused 15 May 2020- restart intended 1/9/2020 - 80% complete. Remaining works to recommence 1 Sep 2020 to complete Autumn 20 (aligned to work schedule). | N/A | Bird nesting resulted in up to 80% work completed- restart as soon as WS amended. | Licensable works paused 15 May 2020- restart intended 1/9/2020 - 90% complete. Remaining works to recommence 1 Sep 2020 to complete Autumn 20 (aligned to work schedule).
14 | (If available,) Please supply us with a list of the a list of all persons authorised to act under the licence and in what capacity (i.e. Accredited Agent or Assistant); | Attached | Attached | N/A | Attached | Attached
15 | Have there been any conflicts with Members of the public when undertaking the licensable activities? E.g. any tampering with exclusion devices? | N/A | Held up access to the site on a number of occasions | N/A | No | No
16 | Has the presence of any other protected species impeded clearance works? | N/A | Nesting birds only | N/A | Nesting birds only | Nesting birds only