## Kenilworth WML-OR53
Date | Species | Number | Location |  | Tree roost details | Licence action | Number captured/transported | NE informed? (Condition B15) | Method of informing NE | Comments | Surveyor
2020-05-04 | Soprano pipistrelle | 1 | 52.3729 | -1.5905 | n/a | n/a | 1 | Matt Wisdom of LM informed NE on 07/05/2020 | Email | This bat was found in a brash pile by no bat ECOWs searching for bird nests. No works in this area had taken place for a number of weeks. The bat was injured beyond recovery and was euthanised following assessment by bat carer.
2020-05-12 | Daubenton's | 1 | 52.3719 | -1.587 | Oak tree- Split in branch creating wedge shaped cavity | Not able to access bat, left for further inspection | 0 | 2020-05-14 | Email | This bat was located after a second inspection of the tree by another AA. The feature was re-inspected on 13/05/2020 and the bat could not be seen in the same poistion. However the cavity could not be fully inspected and the tree has been retained.
2020-05-12 | Daubenton's | 3 | 52.3727 | -1.5903 | Cavity in birch tree | One way excuder fitted on the 12/05/2020 | 0 | 2020-05-14 | Email | 3 x Daubenton's observed in cavity. Emergence video on the 12/05/2020 observed one bat emerge from the one way excluder within the first 90 minutes after sunset. A resinspection on the 13/05/2020 found no bats in the cavity which could be fully inspected. It was assumed that the other bats emerged from the tree later that night. The tree was subsequently felled on 13/05/2020.

## Marlowes WML-OR56
Encounter reference | Date encountered | Species | Number | Location |  | Tree roost details | Licence action | Number captured/transported | NE informed? (Condition B15) | Method of informing NE | Comments | Surveyor
1 | 2020-04-10 | Daubenton's | 2 | 52.4075 | -1.6572 | Sycamore cavity | Not able to access bats, left for further inspection | 0 | 2020-04-11 | Email | Bats still in tree on 17/04/2020- exclusion process started 18/04/2020- bat emergence on 18/04/2020 showing both daubenton's exited roost. Re-inspected PRF on the 19/04/2020, no bats present and tree declared free of bats and tree felled on 19/04/2020.
2 | 2020-04-15 | Brown long-eared | 1 | 52.4078 | -1.6608 | Sycamore cavity | Not able to access bats, left for further inspection | 0 | 2020-04-19 | Email | Bat had left roost on own accord by 17/04/2020 roost outside clearance area - tree retained.
3 | 2020-04-16 | Brown long-eared | 1 | 52.408 | -1.6597 | Sycamore cavity | Tree climbed and cleared. Bat found after tree was felled | 1 | 2020-04-19 | Email | Bat suffered minor injury and was taken into care. Took food and water and was test flown prior to successful release on evening of 19/04/2020 at Marlowes.
4 | 2020-04-18 | Daubenton's | 1 | 52.4078 | -1.6588 | Sycamore cavity | Not able to access bats, left for further inspection | 0 | 2020-04-19 | Email | Tree reinspected on 19/04/2020, no bats present and tree declared free of bats and was felled same day.
5 | 2020-04-18 | Leisler's | 1 | 52.4075 | -1.6572 | Sycamore cavity | Not able to access bats, left for further inspection | 0 | 2020-04-19 | Email | This Leisler's bat was found roosting with the two Daubenton's bats on the 18 April. It was also excluded along with the Daubenton's bats on the evening of 18/04/2020. Tree inspected on 19/04/2020, no bats present and decleared free of bats (see reference 1)
6 | 2020-04-20 | Natterer's | 1 | 52.4079 | -1.6588 | Sycamore cavity | Not able to access bats, left for further inspection | 0 | 2020-04-22 | Email | Natterer's bat was left in the roost following inspection. Re-inspection in 21 April revealed that the bat had left the roost over night. The roost was felled on 21 April 2020.
7 | 2020-04-20 | Unknown bat species | 2 | 52.4079 | -1.6588 | Woodland | Indirect disturbance | 0 | 2020-04-22 | Email | Two bats were observed flying in the canopy adjacent to tree works. The trees being felled had been inspected with no sign of bats, and the Natterer's bat found was still in its roost. Felling ceased and trees in the area re-inspected with no evidence of roosting bats. Nats were not seen to roost in nearby trees. Likely indirect disturbance of trees outside immediate works area.
8 | 2020-04-23 | Common pipistrelle | 2 | 52.4082 | -1.6587 | Unknown dead tree species - Callus roll | Not able to access bats, left for further inspection | 0 | 2020-04-27 | Email | The 2 x common pipistrelle bats were left in situ after inspection on 23 April. Roost location was inspected on 24 April 2020 and the bats had vacated the tree/roost feature. The tree was felled on 24 April 2020.
9 | 2020-04-24 | Common pipistrelle | 1 | 52.4081 | -1.6586 | Sycamore cavity | Not able to access bats, left for further inspection | 0 | 2020-04-27 | Email | This common pipistrelle was left in situ after inspection. Reinspection on 25 April 2020 confirmed the bat had left the roost on its own accrod. Tree felled after confirmed clear of bats.
10 | 2020-04-24 | Common pipistrelle | 1 | 52.4082 | -1.6588 | Callus roll on branch - Sycamore | Not able to access bats, left for further inspection | 0 | 2020-04-27 | Email | Common pipistrelle found in feature unsafe to exclude and not able to capture bat. Inspection on 25 April 2020 revealed this bat had vacated this roost feature. However another roost feature on same tree was found to be in use by the same species (possible the same bat) See ref 11. The roosting feature was carefully dismatled to prevent re-use.
11 | 2020-04-25 | Common pipistrelle | 1 | 52.4082 | -1.6589 | Callus roll on branch - Sycamore | Not able to access bats, left for further inspection | 0 | 2020-04-27 | Email | Same tree as ref 10 above. However found in different roost site on another dead limb - Update - bat vacated on own accord on 27 April 2020 and PRF felled
12 | 2020-04-26 | Daubenton's | 1 | 52.4076 | -1.6576 | Callus roll on branch - Sycamore | Not able to access bats, left for further inspection | 0 | 2020-04-27 | Email | Due to be re-inspected on 27 April 2020- Update -bat vacated on own accord on 27 April 2020 and PRF felled
13 | 2020-04-26 | Leisler's | 1 | 52.4075 | -1.6579 | Dead limb on Oak tree | Not able to access bats, left for further inspection | 0 | 2020-04-27 | Email | Due to be re-inspected on 27 April 2020 - Update - bat vacated on own accord on 27 April 2020 and PRF felled.
14 | 2020-04-28 | Natterer's | 1 | 52.4082 | -1.6588 | Callus roll on branch - updward facing limb - Sycamore | Not able to access bats, left for further inspection | 0 | 2020-05-04 | Email | Bat was still in situ on 29 April and tree was reatined. Final tree PRF works to Marlowes on 30 April. This tree was reatined at end of this part of the licence period. No more licensable works at Marlowes from 1 May 2020.

## Ash Beds WML-OR55
Date | Species | Number | Location |  | Tree roost details | Licence action | Number captured/transported | NE informed? (Condition B15) | Method of informing NE | Comments | Surveyor
2020-06-02 | Common pipistrelle | 1 | 52.2968 | -1.469 | Large trunk cavity at base in oak tree. | Not able to access bat, roost left in situ requires destructive search | N/A | 2020-06-06 | Email | Bat was observed during barn owl survey of tree cavity. It cralwed out of sight so 100% identification could not be made, but considered to be a pipistrelle from what was observed. Tree has been reatined and will be subject to further surveys.
2020-06-04 | Common pipistrelle | 1 | 52.2954 | -1.4672 | Cavity in ash tree | Bat taken by hand and relocated to cavity bat box | 1 | 2020-06-06 | Email | Bat was healthy and checked over prior to being transported to a cavity bat box at 52.296784, -1.472793 within the reatiend Ash Beds woodland- roost tree felled same day
2020-06-07 | Common pipistrelle | 1 | 52.2954 | -1.467 | Cavity in ash tree | Bat left in situ and excluder fitted on 7 June 2020 | 0 | 2020-06-13 | Email | The feature was re-inspected the following morning (08/06/2020) and the roost was confirmed as clear of bats. The tree was immediately felled.
2020-06-09 | Natterers | 1 | 52.2953 | -1.465 | Cavity in ash tree | Bat left in situ and excluder fitted on 9 June 2020 | 0 | 2020-06-13 | Email | The feature was re-inspected the following morning (10/06/2020) and the roost was confirmed as clear of bats. The tree was immediately felled.
2020-06-16 | Common pipistrelle | 1 | 52.2955 | -1.4666 | Cavity in ash tree | Bat left in situ and excluder fitted on 16 June 2020 | 0 | 2020-06-23 | Email | The feature was re-inspected the following morning (17/06/2020) and the roost was confirmed as clear of bats. The tree was immediately felled.